Activity 3 Worked solutions: Calculating unit rates

Item a

Using the information provided on the Activity 3 Reference sheet calculate the unit rate for:

Foundation excavation not exceeding 2 m deep.

Plant

Excavator			0.2 hours × £36.30 per hour =		£7.26

Labour

Excavator driver			0.2 hours × £24.60 per hour =		£4.92

Banksman 			0.2 hours × £20.50 per hour = 		£4.10

___________

Total (unit rate)  							      =		£16.28		per m3

___________

Item b

Using the information provided on the Activity 3 Reference sheet calculate the unit rate for:

A142 mesh reinforcement 2.22 kg per m2, minimum 300 mm side and end laps.
(There is no plant required for this item)

Materials

A142 mesh   35.00 per sheet ÷ (4.8 × 2.4) = £35.00 ÷ 11.52	=	£3.04

+  22.5% waste	£0.68

Spacer blocks/chairs				5 No 	× 	£0.70  	= 	£3.50

+  5% waste	£0.18

Tie wire				9 length × 	£0.03 	= 	£0.27

+  5% waste	£0.01

________

Sub-total materials								£7.68

Labour

Steel fixer 				0.15 hours x £26.30	=	£3.95

________

Total (unit rate)							=	£11.63 	per m2

________

Item c

Using the information provided on the Activity 3 Reference sheet calculate the unit rate for:

One brick wall in type B facings, in 1:1:6 mortar, pointed both sides as the work proceeds.

Materials

Bricks (£722.00 ÷ 1000 = £0.72 each) 		119 No × £0.72	=	£85.68

Mortar				0.054 m3 × £125.00		=	£6.75

_________

Sub-total materials									£92.43

+  7.5% waste		£6.93

Labour

Bricklayer				2.8 hours × £28.75		=	£80.50

Labourer				1.4 hours × £19.50		=	£27.30

_________

Total (unit rate)								=	£207.16 	per m2

_________