## Slide 1: Construction
Topic: Calculating construction costs
Route: Construction
Lesson 1: Calculating unit rates
Notes: Image © Shutterstock/Dragon Images

## Slide 2: In this lesson, we will:
Identify the different costs involved in a construction project
Outline the roles of a quantity surveyor and an estimator
Calculate material and labour costs
Calculate unit rates
Skills:
CS3 Follow standard processes to produce unit rates, bills of quantities and their costing documentation
General competencies:
English:
E2 Present information and ideas
E5 Synthesise information
Maths:
M2 Estimate, calculate and spot errors
M3 Work with proportion
M4 Use rules and formulae
M5 Process data
M8 Communicate using mathematics
M9 Cost a project
Digital:
D3 Communicate and collaborate
Introduction
Lesson 1: Calculating unit rates

## Slide 3: What do you know about costs?
Lesson 1: Calculating unit rates
Introduction
Notes: Image © Shutterstock/Dragon Images

## Slide 4: What construction costs can you think of?
List the costs that you think a building site might generate.
In small groups, collate your lists and categorise them into different types of costs.
Lesson 1: Calculating unit rates
Introduction
Notes: Image © Pexels/CK Seng

## Slide 5: Different construction costs
Lesson 1: Calculating unit rates
Material costs: expenses associated with purchasing and delivering to site. For example, bricks, concrete, steel and insulation.
Labour costs: rates paid to construction workers and tradespeople plus any additional costs of employment.
Preliminary costs: costs that are not covered in the measured work section of a Bill of Quantities (BoQ). Includes things before, during and after the project. For example, site setup, site fencing, site accommodation, site supervision, scaffolding, final cleaning, commissioning and handover.
Introduction
Plant costs: the use of machinery and equipment needed on a construction site, including hire/purchase of items such as excavators, cranes and tools.

## Slide 6: Cost management and NRM 2
Lesson 1: Calculating unit rates
Component | Included | Unit | Pricing method | Excluded
1 Testing and commissioning plan. | Costs associated with the following shall be deemed to be included in section 1.2.1: Management and staff costs: 1 Preparation of Commissioning Plan. | item | 1 Fixed charge 2 Time-related charge | 1 Testing and commissioning of services.
Handover. | Unless otherwise indicated, costs associated with the following shall be deemed to be included in section 1.2.1: Management and staff costs: 1 Preparation of Handover Plan. |  |  | 
 | 2 Training of building user’s staff in the operation and maintenance of the building engineering services systems. |  |  | 
 | 3 Provision of spare parts for maintenance of building and engineering services. |  |  | 
 | 4 Provision of spare parts and portable indicating instruments for the operation and maintenance of building engineering services systems. |  |  | 
 | 5 Pre-completion inspections. |  |  | 
 | 6 Final inspections. |  |  | 
This is an extract from the New Rules of Measurement 2 (NRM 2). NRM provide a standard set of measurement rules that can be applied to any project.
Preliminary costs are extensive and are detailed in the NRM.
Introduction
Notes: Extract from RICS New Rules of Measurement NRM 2 ISBN 9781842197165

## Slide 7: How and why are costs monitored?
Valuations are carried out monthly.
These valuations help determine interim payments.
The BoQ can be used to complete a valuation.
Variations are included in the valuation.
A retention percentage can be deducted and retained, by the client, until the project is completed.
Lesson 1: Calculating unit rates
Introduction
Notes: Image © Unsplash/Glenov Brankovic

## Slide 8: What if the scope of work changes?
A variation is a change to the original scope of work. These can be modifications to design, materials, construction methods or project timelines.
It is important that changes are documented and agreed upon to manage costs and project quality effectively.
The architect or supervising officer usually give instructions about variations to the contracted works.
Reasons for a variation:
changes to design
unforeseen conditions, e.g. unexpected ground conditions
client requests
change in nominated subcontractors
adjustments needed to meet building control requirements.
changes in the law
inflation.
Lesson 1: Calculating unit rates
Introduction

## Slide 9: Why do we need to monitor costs?
Understanding costs is essential for estimating and controlling budgets.
Controlling costs is important to ensure a project stays on budget and meets its financial objectives.
Mismanagement of resources can lead to delays, increased expenses, and financial strain on the contractor and the client.
Lesson 1: Calculating unit rates
Introduction
Notes: Image © Pexels/Pixabay

## Slide 10: What factors can impact costs and profits?
Challenges
Increased cost of materials, labour, energy.
Harder to find skilled workers.
Biodiversity Net Gain (BNG) and the Building Safety Act (BSA) add more responsibilities.
Outcomes of challenges
Building residential and commercial property is more expensive and harder to manage.
Rules add cost but do not increase value of homes being built, making it difficult to make a good profit.
Lesson 1: Calculating unit rates
Think about the construction of a new residential building or commercial space.
Introduction

## Slide 11: How can we manage these challenges?
Planning ahead and using accurate data can help keep projects on track, even when costs and rules are changing.
A careful approach can help ensure projects end successfully and stay profitable.
An estimator, buyer and quantity surveyor all play a role in the estimation and control of costs on construction projects.
The contract will set out whether the client or the contractor is responsible when costs are changing.
Lesson 1: Calculating unit rates
Introduction
Watch this video about estimating construction costs and make notes using the Introduction worksheet.
Notes: Image © Pexels/Mohamed Hamdi
Estimating construction costs video: https://vimeo.com/1104064715/e1cf2c67fc

## Slide 12: Quantity surveyor interview
Lesson 1: Calculating unit rates
Activity 1
Watch this video about the role of a quantity surveyor and make notes using the Activity 1 worksheet.
Notes: Role of a quantity surveyor video: https://vimeo.com/1104064839/4c215420ba

## Slide 13: What does a QS do?
The QS plays an important role in managing both the financial and contractual aspects of a construction project, ensuring smooth progress from start to finish.
The QS can work for clients or contractors.
Lesson 1: Calculating unit rates
Activity 1
Notes: Image © Pexels/Thirdman

## Slide 14: Responsibilities of a QS
The role of a QS begins at the planning stage. They help develop a detailed budget based on estimates detailed in the scope of work. They ensure that the costs are realistic and align with the overall objectives of the project.
Once construction begins, the QS monitors ongoing expenses through valuations.
They keep track of the variations and advise the client on potential financial risks or opportunities.
Lesson 1: Calculating unit rates
Activity 1

## Slide 15: What does an estimator do?
The estimator is a key member of the team. They are responsible for calculating the cost estimate and price before construction begins.
They need to include all direct costs (e.g. labour, plant, materials) and indirect costs (e.g. supervision, office facilities, insurance, overheads and profit).
Lesson 1: Calculating unit rates
Activity 1
Notes: Image © Unsplash/Jakub Zerdzicki

## Slide 16: Labour costs
Many trades work together on a construction site.
The cost of using each trade varies.
Costs are dependent on the required skill level, and whether professional qualifications are needed.
Lesson 1: Calculating unit rates
Make a list of all the trades that may be involved in a building project.
Rank your list from those which you think cost the most, to the least.
Activity 2

## Slide 17: Labour costs
Lesson 1: Calculating unit rates
Trade | Hourly rate
Electrician | £40–70
Plumber | £40–60
Gas engineer | £40–50
Joiner/Carpenter | £30–45
Painter/Decorator | £30–45
Plasterer | £37–50
Roofer | £35–40
Bricklayer | £30–40
Labourer | £14–45
Plant operator | £14–20
Activity 2
Notes: Image © Pexels/Trinh Tran
Please note, the rates shown are taken from: www.checkatrade.com/blog/cost-guides/how-much-do-tradespeople-cost/ and: www.jobsite.co.uk/jobs/plant-operator
Rates (as of April 2025) from:
https://www.checkatrade.com/blog/cost-guides/how-much-do-tradespeople-cost/
https://www.jobsite.co.uk/jobs/plant-operator

## Slide 18: All-in labour rates
All-in labour rates cover all the incidental costs of employing a construction operative, not just the pay that the operative receives.
All-in labour rates are calculated each year when pay agreements are settled.
The Construction Industry Joint Council (CIJC) Working Rule Agreement (WRA) sets out standard rates for the construction industry.
The National Agreement for the Engineering Construction Industry (NAECI) sets terms and conditions of employment throughout the UK.
Incidental costs include:
inclement weather allowance
non-productive overtime costs
employers’ National Insurance Contributions (NIC)
sick pay allowance
Construction Industry Training Board (CITB) levy contributions
holiday credits
pension contributions
other allowances.
Lesson 1: Calculating unit rates
Activity 2

## Slide 19: All-in labour rate: Calculation example
This table shows an example of the calculation of an all-in labour rate.
It covers all the incidental costs of employing a construction operative.
Lesson 1: Calculating unit rates
Guaranteed minimum wages Contractor’s bonus allowance Inclement weather allowance (included via adjustment to working hours) Non-productive overtime costs Sick pay allowance Trade supervision Working Rule Agreement allowances (generally for labourers not craft operatives) Sub-total | £28,920 £3,219 – £1,007 £203 £1,740 – £35,089
CITB training contributions (0.35% on annual payroll £35,089) National Insurance Contributions (15% of average earnings £675 × 52wks) Holiday credits Tool allowances Sub-total | £123 £5,265 £4,172 £225 £44,874
Severance payments (2% of labour costs) Sub-total | £897 £45,771
Employer’s liability insurance (2% of labour costs) Annual cost per craft operative Number of productive hours worked All-in hourly rate (n ÷ o) | £915 £46,686 1834 £25.46
Activity 2
Notes: Table from The Chartered Institute of Building Code of Estimating Practice 7th Edition (2009) ISBN 9781405129718 (modified to reflect increases in labour costs up to February 2025)

## Slide 20: Examples of construction plant machinery
Excavator: for excavating foundations.
Concrete mixer: for mixing concrete and mortars.
Scaffolding: fixed access for working at height.
Scissor lift: mobile access to high areas.
Mobile crane: lifting heavy loads on large projects.
Plate compactor: for compacting soil or gravel for sub-bases.
Mobile generator: temporary power supply on site.
Lesson 1: Calculating unit rates
Activity 2
Notes: Image © Pexels/Jimmy Nilsson Masth

## Slide 21: Plant costs
Lesson 1: Calculating unit rates
What are these different types of machine used for?
Plant and equipment | Daily hire cost (£) | Weekly hire cost (£)
Excavator (mini) | £150 | £675
Concrete mixer | £50 | £225
Scaffolding | £100 | £450
Scissor lift | £120 | £540
Mobile crane | £300 | £1,350
Plate compactor | £45 | £180
Mobile generator | £50 | £225
Activity 2
Notes: Please note, the rates shown are taken from: www.checkatrade.com/blog/cost-guides/how-much-do-tradespeople-cost/ and: www.jobsite.co.uk/jobs/plant-operator

## Slide 22: Materials costs
Lesson 1: Calculating unit rates
Material type | Unit | Cost per unit | Coverage rate | Waste percentage
Paint | 1 litre | £15 | 10 m2 per litre | 10%
Render (25 mm thick) | 1 m3 | £200 | 0.025 m3 per square metre | 5%
Bricks | 1000 bricks | £450 | 16 m2 per metre | 2%
Blocks | 1 m2 | £15 | 98 m2 per 1000 | 5%
Paving slabs (600 mm × 600 mm) | 1 slab | £12 | 2.78 slabs per square metre | 5%
Cavity wall ties | 250 ties | £100 | 4 ties per square metre | 2%
Cement mortar (for a one brick wall) | 1 m3 | £5 | 0.054 m3 per square metre | 5%
Activity 2
Notes: Please note, the rates shown are taken from: www.checkatrade.com/blog/cost-guides/how-much-do-tradespeople-cost/ and: www.jobsite.co.uk/jobs/plant-operator

## Slide 23: Unit rate
A unit rate refers to the cost per unit of measurement (for example £ per m3 of concrete).
The unit rate calculation includes material costs, wastage, labour and sometimes overhead or plant costs.
It helps contractors and quantity surveyors estimate costs efficiently and compare prices for different construction elements.
Lesson 1: Calculating unit rates
Activity 3
Notes: Image © Unsplash/Microsoft 365

## Slide 24: Coverage and wastage
Coverage This is the amount of material needed to cover a specific area or complete a given task. For instance, 60 bricks are required to build 1 m2 of half brick wall.
Wastage This refers to the extra materials accounted for in calculations due to losses during transportation, laps, cutting, theft or accidental damage on-site.
Typically, a percentage is added to the required materials to account for this.
Lesson 1: Calculating unit rates
When calculating unit rates, coverage and wastage must be considered.
Activity 3

## Slide 25: Labour constants
A labour constant is the time needed for a construction operative to complete the work required for one unit of measurement, e.g. 1 m2 of brickwork. They are used to estimate unit rates.
Labour constants remain the same, but costs per hour can change.
In computer estimating systems, labour constants are embedded. The hourly cost to employ can be input by the estimator.
Lesson 1: Calculating unit rates
Activity 3
Notes: Image © Unsplash/Solomen

## Slide 26: Calculating a unit rate
Lesson 1: Calculating unit rates
Activity 3
Notes: Unit rate calculation explainer video: https://vimeo.com/1103437896

## Slide 27: Calculating a unit rate: Brickwork
This is an extract from a BoQ which is a document used for pricing and tendering.
We will see how to ‘build up’ a unit rate for this item.
Lesson 1: Calculating unit rates
Item | Description | Quantity | Unit | Unit rate | Total
a | Half a brick wall in type A facings, in coloured mortar, in skins of hollow walls, pointed one side as the work proceeds | 1251 | m2 |  | 
Activity 3
Notes: Image © Pexels/Mike Bird

## Slide 28: Worked example: Brickwork unit rate
Hint
To calculate waste, multiply the total cost of your materials by the wastage factor, in this example it is 5%.
This is then added to the total cost.
Lesson 1: Calculating unit rates
Materials |  | 
Bricks | 60 No × £0.64 = | £38.40
Mortar | 0.027 × £150 = | £ 4.05
Subtotal |  | £42.45
Waste (+ 5%) | £42.45 × 0.05 = | £ 2.12
Subtotal (materials) |  | £44.57
Labour |  | 
Bricklayer | 1.4 hours × £28.75 = | £40.25
Labourer | 0.7 hours × £19.50 = | £13.65
Total |  | £98.47 per m2
Activity 3

## Slide 29: Calculating the total cost
The unit rate we calculated is the cost of completing 1 m2 of the brickwork.
This rate (£98.47 per m2) can be inserted into the BoQ and multiplied by the quantity to produce a total.
Lesson 1: Calculating unit rates
Item | Description | Quantity | Unit | Unit rate | Total
a | Half a brick wall in type A facings, in coloured mortar, in skins of hollow walls, pointed one side as the work proceeds | 1251 | m2 | £98.47 | £123,185.97
Activity 3
Notes: Image © Pexels/Mike Bird

## Slide 30: Calculating a unit rate: Forming cavities
This is an extract from a BoQ.
We will see how to ‘build up’ a unit rate for this item.
Lesson 1: Calculating unit rates
Item | Description | Quantity | Unit | Unit rate | Total
b | Forming 100 mm cavity in hollow walls, 4 No type A stainless steel wall ties per m2 | 1245 | m2 |  | 
Activity 3
Notes: Image © Shutterstock/Radovan1

## Slide 31: Worked example: Forming cavities
Remember, when calculating, round results to the nearest penny (2 decimal places).
Lesson 1: Calculating unit rates
Materials |  | 
Wall ties | 4 No × £1.75 = | £7.00
Waste (+ 2.5%) | £7.00 × 0.025 = | £0.18
Subtotal (materials) |  | £7.18
Labour |  | 
Bricklayer | 0.1 hours × £28.75 = | £2.88
Labourer | 0.05 hours × £19.50 = | £0.98
Total |  | £11.04 per m2
Activity 3

## Slide 32: Computerised estimating systems
Technology has revolutionised construction estimating and now digital BoQ are commonly used.
Computerised estimating systems calculate the unit rates, but the estimator will:
input material prices and plant hire rates;
fine-tune waste percentages;
review embedded labour constants;
input all-in labour rates;
add a percentage to each item for overheads and profit.
Lesson 1: Calculating unit rates
Activity 3
Notes: Image © Unsplash/Glenn Carstens-Peters

## Slide 33: Calculating unit rates: Practice
Working as a pair/team complete the questions on the worksheet.
Lesson 1: Calculating unit rates
Resources:
L1 Activity 3 Reference sheet
L1 Activity 3 Worksheet
Calculator
Activity 3

## Slide 34: Calculating unit rates: Answers
Practice exercise unit rate (a)
£16.28 per m3
Practice exercise unit rate (b)
£11.63 per m2
Practice exercise unit rate (c)
£207.16 per m2
Lesson 1: Calculating unit rates
Activity 3
Resources:
L1 Activity 3 Worked solutions

## Slide 35: How can a contractor reduce project costs?
Adopt modern methods of construction: Using prefabricated, modular construction and off-site manufacturing helps reduce build time, reducing site costs, minimising waste and reducing labour costs.
Value engineering: The design and the materials selected are evaluated to identify cost-effective alternatives without compromising on quality or performance. Value engineering prioritises the essential features of a project and eliminates unnecessary expenses.
Lesson 1: Calculating unit rates
By minimising waste and using materials wisely, a contractor will make a project more sustainable which will support the environment.
Activity 3
Notes: Image © Pexels/Kaboompics.com

## Slide 36: How can a contractor reduce project costs?
Lesson 1: Calculating unit rates
Using skilled and fully trained labour reduces waste associated with mistakes and errors. Skilled labour may be able to complete work more quickly.
Using digital tools such as Building Information Modelling (BIM) to plan the construction sequence and identify potential clashes. For example, between the building’s structural frame and services, reducing errors on site which ultimately saves time and therefore cost.
Bulk buying materials negotiating better terms with suppliers.
Source materials locally reducing transportation costs.
Activity 3
Notes: Image © Pexels/cottonbro studio

## Slide 37: Plenary
What challenges did you face in calculating costs?
Write down three top tips you should remember when performing a unit rate calculation.
Share your tips with a partner. Together, create a final list of three to five tips that includes the most important points from each of your notes.
Lesson 1: Calculating unit rates
Plenary
Notes: Image © Pexels/Engin Akyurt

## Slide 38: In this lesson, we have:
Identified the different costs involved in a construction project
Outlined the roles of a quantity surveyor and an estimator
Calculated material and labour costs
Calculated unit rates
Plenary
Lesson 1: Calculating unit rates
Skills:
CS3 Follow standard processes to produce unit rates, bills of quantities and their costing documentation
General competencies:
English:
E2 Present information and ideas
E5 Synthesise information
Maths:
M2 Estimate, calculate and spot errors
M3 Work with proportion
M4 Use rules and formulae
M5 Process data
M8 Communicate using mathematics
M9 Cost a project
Digital:
D3 Communicate and collaborate

## Slide 39: Consolidation
You and your partner have been assigned the task of calculating the cost of raking out and repointing a section of brick wall.
The consolidation worksheet gives the area of repointing and the labour constants, labour rates, materials cost and coverage.
Consolidation
Lesson 1: Calculating unit rates
Example of mortar joints requiring repointing
Notes: Image © Shutterstock/Nigel Burley