Activity 3: Making decisions

In this activity, you will practise making decisions about which team members to assign to which tasks and determining the optimal flow of work. In small groups, cut out the team profiles and project tasks. Then work together to try to match tasks to the most appropriate team member and determine the logical sequence in which they should be completed.

The decisions you need to make won’t always be easy; sometimes there may be multiple team members suitable for one task and none suitable for others. Use this as an opportunity to identify skill gaps and make a plan for how you might fill them. For example, will you assign an existing team member and provide training or will you fill the gap with a subcontractor?

Scenario:

Your team has been tasked with developing ‘EduConnect’, an innovative online learning platform. Features include:

- interactive courses: engaging video lectures, quizzes and assignments

- personalised learning paths: tailored recommendations based on student progress and interests

- collaborative tools: virtual classrooms, discussion forums and real-time collaboration features

- gamification: badges, leaderboards and other elements to motivate and engage learners

- analytics dashboard: detailed insights into student performance and engagement.

Things to consider:

- Which task(s) must be completed before another can start?

- What are the strengths of each team member?

- What are the interests and career goals of each team member?

- Who is suitable for this role? Will any team members need a supervisor?

- Which team members will be more costly? When considering this question, think about how long they will take to complete the task.

- Will any tasks require input from more than one member of the team?

REMEMBER: There will be multiple ways that you can assign these tasks among the team. The most important thing is that you can justify the decisions you make about who completes the task and when it is scheduled.

Project tasks

| Task: Develop core functionality Description: Build the platform and core features: - User authentication - Course creation and management - Content delivery - Progress tracking | Task: User interface design Description: Craft an intuitive and visually appealing interface that enhances the user experience. | Task: Data storage and retrieval Description: Design and implement a robust database to store and manage user data, course content and analytics. | Task: Testing and quality assurance Description: Thoroughly test all aspects of the platform, including functionality, usability, performance, security and compatibility across different browsers and devices. |
| --- | --- | --- | --- |
| Task: User documentation Description: Create comprehensive guides and tutorials to help users navigate and utilise the platform effectively. | Task: Gamification Description: Design and implement engaging gamification elements to motivate and reward learners. | Task: Analytics dashboard Description: Build a dashboard to provide educators with valuable insights into student performance and engagement. | Task: Personalised learning engine Description: Develop an algorithm to recommend relevant courses and content based on student data. |

Team profiles

| Name: Alex Johnson Experience: 10 years in software development. Proficient in multiple programming languages Strong debugging skills Likes: Mentoring younger developers Full-time – £60/hour | Name: Emi Patel Experience: Recent Computer Science graduate Familiar with basic programming concepts Likes: Working as part of a team Full-time – £45/hour | Name: Daejun Kim Experience: Background in graphic design/UX Proficient in design tools Likes: Creating visually appealing and user-friendly interfaces Collaborating with developers Part-time – £30/hour | Name: Sima Lee Experience: Experienced working with databases and data structures Proficient in data manipulation and visualisation tools Likes: Getting insight from data to inform decision-making Full-time – £50/hour |
| --- | --- | --- | --- |
| Name: Chris Wilson Experience: Experienced in software testing/QA Likes: Tasks that involve being detail-oriented and methodical Full-time – £40/hour | Name: Janina Brown Experience: Senior developer with extensive technical expertise Experienced team leader Likes: Overseeing projects to ensure they meet requirements Full-time – £75/hour | Name: Kevin Nguyen Experience: Some experience with front-end development (HTML, CSS, JavaScript) Basic understanding of UX Likes: Working on visual aspects of projects Part-time – £35/hour | Name: [SUBCONTRACTOR] Write the skills/experience you’re looking for below Experience: Rate: £90/hour Contract Type: Fixed 40-hour contract for specific task |

Note that the subcontractor profile has a rate and contract type specified. This is to prompt students to weigh up the costs and benefits of hiring a highly specialised external resource versus upskilling an internal employee.