Activity 4 Create your own Gantt chart

In groups, you are going to plan the installation of a modular extension to a primary school.

The project must include renewable energy (solar PV), water conservation (rainwater harvesting), and be completed during the 30-day summer holiday period.

You have been given the following high-level schedule, which outlines tasks and durations.

| Task description | Duration |
| --- | --- |
| Site preparation & groundworks | 5 days |
| Delivery of modular units (including crane hire) | 2 days |
| Assembly of modular units on site | 7 days |
| Installation of solar PV system | 3 days |
| Installation of air source heat pump | 2 days |
| Installation of rainwater harvesting tank | 3 days |
| Internal fit-out (lighting, plumbing, finishes) | 5 days |
| Testing & commissioning (by manufacturers) | 2 days |
| Final inspection & handover | 1 day |

- Plan what you need to cover under these headings:

- Project title

- Key phases

- Trades involved

- Task dependencies

- Describe how your plan connects to wider industry considerations in order to create your supporting statement.

| Health and safety |  |
| --- | --- |
| Specialist equipment |  |
| Contractors and job roles |  |
| Waste management |  |

c. Create a Gantt chart showing the sequence of tasks, durations and dependencies.