## Slide 1: Engineering and Manufacturing: Core
Topic: Project management
Lesson 2: Constraints, risks and collaboration
Route: Engineering and Manufacturing
Notes: Image © Shutterstock/Gorodenkoff

## Slide 2: In this lesson we will:
define a project constraint and explain the potential impact of changes to one constraint on others;
estimate the cost of a project and ensure it remains within budget;
interpret a basic risk register;
identify benefits of effective team collaboration in a project environment.
Skills:
CSA. Planning and scoping project parameters (e.g. timescales, resources, costs)
CSB. Interpreting and using technical information and media
CSC. Complying with the requirements and needs of a client’s brief
General competencies:
English:
EC4. Summarise information/ideas
EC5. Synthesise information
EC6. Take part in/lead discussions
Maths:
MC2. Estimating, calculating and error spotting
MC9. Costing a project
Introduction
Lesson 2: Constraints, risks and collaboration

## Slide 3: Recap quiz
Which of the following is an example of an operational requirement in a project brief?
Machine must integrate with the existing conveyor system
Machine must not expose any moving internal parts
Machine must stay within budget
Introduction
Lesson 2: Constraints, risks and collaboration

## Slide 4: Recap quiz
Which of the following is an example of an operational requirement in a project brief?
Machine must integrate with the existing conveyor system
Machine must not expose any moving internal parts
Machine must stay within budget
Machine must integrate with the existing conveyor system
B is a safety requirement and C is a constraint.
Lesson 2: Constraints, risks and collaboration
Introduction

## Slide 5: Recap quiz
Which type of digital tool is used to plan out a whole project?
Risk register
Gantt chart
Cost spreadsheet
Lesson 2: Constraints, risks and collaboration
Introduction

## Slide 6: Recap quiz
Which type of digital tool is used to plan out a whole project?
Risk register
Gantt chart
Cost spreadsheet
B. Gantt chart
A risk register is used to reduce the likelihood of anyone being harmed. A cost spreadsheet is used to keep track of the total amount of the budget spent.
Lesson 2: Constraints, risks and collaboration
Introduction

## Slide 7: Recap quiz
During which stage of a project life cycle are outcomes reflected on and improvements considered?
Evaluation
Planning
Implementation
Lesson 2: Constraints, risks and collaboration
Introduction

## Slide 8: Recap quiz
During which stage of a project life cycle are outcomes reflected on and improvements considered?
Evaluation
Planning
Implementation
Evaluation
Planning is carried out at the start of a project and involves scheduling and resource planning. Implementation is the stage where a product is built and tested.
Lesson 2: Constraints, risks and collaboration
Introduction

## Slide 9: Project constraints
In your groups:
list typical project constraints;
group the constraints into categories such as:
  resources;
  quality.
Lesson 2: Constraints, risks and collaboration
Activity 1

## Slide 10: Project constraints
Constraints are the limits you must work within. Typical constraints include:
budget (keeping the project under a certain amount of money);
time (deadlines, milestones);
quality (performance, tolerances);
safety (pressure limits, safe operation, legislation);
resources (materials, equipment, staff availability);
communication (meetings, reporting structures);
changing requirements (client updates, new information).
Lesson 2: Constraints, risks and collaboration
Activity 1

## Slide 11: Identifying constraints
Think about an engineering project you have worked on (or are aware of) within an engineering workplace. For example,
HS2 (the high-speed railway from Birmingham to London).
List four specific constraints.
Lesson 2: Constraints, risks and collaboration
Activity 1
Notes: Image © Shutterstock/APChanel

## Slide 12: Workbook
Complete Lesson 2 Activity 1: Cost estimation
Lesson 2: Constraints, risks and collaboration
Activity 1
Notes: Image © Shutterstock/vanitjan

## Slide 13: Risk management
Risk management means identifying what might go wrong, how likely it is, how serious it is and what can be done to reduce the risk.
Common engineering risks include:
being over-budget;
faulty components;
delays in materials;
safety hazards;
miscommunication;
unclear requirements;
time overruns;
reputation.
Lesson 2: Constraints, risks and collaboration
Activity 2
Notes: Image © Shutterstock/Washburn HM

## Slide 14: Risk register
Complete the risk register.
A score of 1 is the highest and 5 is the lowest.
Activity 2
Risk | Likelihood (1–5) | Impact (1–5) | Mitigation action
Delay in materials arriving |  |  | 
Change of specification from the customer |  |  | 
Hard-to-procure items incur an increased cost which takes the project over budget |  |  | 
Lesson 2: Constraints, risks and collaboration

## Slide 15: Risk register – answers
Activity 2
Risk | Likelihood (1–5) | Impact (1–5) | Mitigation action
Delay in materials arriving | 3 | 4 | Order early; identify alternative suppliers; include buffer time in plan.
Change of specification from the customer | 1 | 5 | Ensure clear communication between project management and customer.
Hard to procure items incur an increased cost which takes the project over budget | 2 | 4 | Market research and part / item availability to be conducted early in the planning phase to minimise risk.
Lesson 2: Constraints, risks and collaboration

## Slide 16: Collaborative working
Engineering teams use collaborative working to share tasks, solve problems and complete projects efficiently.
Matrix working: individuals may report to more than one leader (e.g. Project Manager and Technical Lead)
Collaborative technologies: Teams*, Slack**, shared documents, cloud-based CAD, shared Gantt charts
Communication structures: daily check-ins, reporting delays, updating plans
Activity 3
Lesson 2: Constraints, risks and collaboration
Notes: **Teams is a trademark of the Microsoft Corporation. **Slack is a trademark and service mark of Slack Technologies, Inc., registered in the U.S. and in other countries.

## Slide 17: Communication plan
Imagine that you are going to be part of a team designing a new factory machine, which needs to be integrated into a production line in six months.
Write a short plan for how your team should communicate during the project. Think about:
How often will you update each other?
What tools will you use?
Who will report any delays to the Project Manager?
Activity 3
Lesson 2: Constraints, risks and collaboration

## Slide 18: The conveyor belt crisis simulation
A manufacturing plant that produces small plastic components has reported that its automated conveyor system is shutting down intermittently during operation. The shutdowns are causing production delays, missed deadlines and rising costs.
Initial checks suggest that the issue may involve inconsistent component handling, possible sensor misalignment or wear in pneumatic actuators used along the conveyor line. The system must operate continuously during an 8-hour shift, and downtime beyond 48 hours will result in financial penalties from the client.
Your engineering team has been given 48 hours to stabilise the system and present a short plan for repair and control before a full redesign is considered.
Plenary
Lesson 2: Constraints, risks and collaboration

## Slide 19: The conveyor belt crisis simulation
TASK – You have five minutes to complete the three-part Emergency Plan.
Identify the constraints – choose two and be specific.
Scan for risks – identify one major risk and how you will mitigate it.
Plan your team communication. Answer one of these:
How will your team share updates?
Who is responsible for reporting delays?
What collaborative tool will you use?
Plenary
Lesson 2: Constraints, risks and collaboration

## Slide 20: In this lesson, we have:
defined a project constraint and explained the potential impact of changes to one constraint on others;
estimated the cost of a project and ensured it remains within budget;
interpreted a basic risk register;
identified benefits of effective team collaboration in a project environment.
Skills:
CSA. Planning and scoping project parameters (e.g. timescales, resources, costs)
CSB. Interpreting and using technical information and media
CSC. Complying with the requirements and needs of a client’s brief
General competencies:
English:
EC4. Summarise information/ideas
EC5. Synthesise information
EC6. Take part in/lead discussions
Maths:
MC2. Estimating, calculating and error spotting
MC9. Costing a project
Lesson 2: Constraints, risks and collaboration
Plenary