## Project summary
Lesson 5: Gantt chart © Gatsby Technical Education Projects 2026
Key Project Information |  |  | Key personnel | Code
Intended start date | 2026-06-05 |  | Project manager | PM
Requested time scale (Weeks) | 6 |  | Design engineer | DE
Requested time scale (Days) | 42 |  | Build technician | BT
Hours worked per day per Staff member | 7 |  | Health and safety officer | HSO
Task | Estimated number of work hours
Market research | 35
Define specifications | 21
Project planning | 35
Detail design | 14
Prototype build | 21
Prototype testing and evaluation | 14
Design build | 21
Design testing and evaluation | 14
User documentation | 35
Contingency | 14

## Gantt chart
Lesson 5: Gantt chart © Gatsby Technical Education Projects 2026
[7 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 |  |  |  |  | 151 | 152 | 153 | 154 | 155 | 156
Task ID | Task | Dependency | Start Date | End Date | Personnel | Task duration (hours) | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday
[7 empty] | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13
1 | Market research | - | 2026-05-05 | 2026-05-09 | PM | 35 | bar: 2026-05-05 to 2026-05-11; 2026-05-17 to 2026-05-18; 2026-05-24 to 2026-05-25; 2026-06-07 to 2026-06-08
2 | Define specifications | 1 | 2026-05-12 | 2026-05-14 | PM / DE | 21 | bar: 2026-05-10 to 2026-05-14; 2026-05-17 to 2026-05-18; 2026-05-24 to 2026-05-25; 2026-06-07 to 2026-06-08
3 | Project planning | 2 | 2026-05-15 | 2026-05-21 | PM | 35 | bar: 2026-05-10 to 2026-05-11; 2026-05-14 to 2026-05-21; 2026-05-24 to 2026-05-25; 2026-06-07 to 2026-06-08
4 | Detail design | 3 | 2026-05-22 | 2026-05-23 | DE | 14 | bar: 2026-05-10 to 2026-05-11; 2026-05-17 to 2026-05-18; 2026-05-21 to 2026-05-25; 2026-06-07 to 2026-06-08
5 | Prototype build | 4 | 2026-05-26 | 2026-05-28 | BT | 21 | bar: 2026-05-10 to 2026-05-11; 2026-05-17 to 2026-05-18; 2026-05-24 to 2026-05-28; 2026-06-07 to 2026-06-08
6 | Prototype testing and evaluation | 5 | 2026-05-29 | 2026-05-30 | BT / HSO | 14 | bar: 2026-05-10 to 2026-05-11; 2026-05-17 to 2026-05-18; 2026-05-24 to 2026-05-25; 2026-05-29 to 2026-05-30; 2026-06-07 to 2026-06-08
7 | Design build | 6 | 2026-06-02 | 2026-06-04 | BT | 21 | bar: 2026-05-10 to 2026-05-11; 2026-05-17 to 2026-05-18; 2026-05-24 to 2026-05-25; 2026-06-02 to 2026-06-04; 2026-06-07 to 2026-06-08
8 | Design testing and evaluation | 7 | 2026-06-05 | 2026-06-06 | BT/HSO | 14 | bar: 2026-05-10 to 2026-05-11; 2026-05-17 to 2026-05-18; 2026-05-24 to 2026-05-25; 2026-06-05 to 2026-06-08
9 | User documentation | 7,8 | 2026-06-05 | 2026-06-11 | PM/DE/HSO | 35 | bar: 2026-05-10 to 2026-05-11; 2026-05-17 to 2026-05-18; 2026-05-24 to 2026-05-25; 2026-06-05 to 2026-06-11
| Contingency |  |  |  |  | 14 | bar: 2026-06-12 to 2026-06-13