Workbook (teacher version) – 
Pneumatic gripper arm project

1. Introduction and industry context

Apex Robotics has reported that their existing pneumatic gripper is causing damage to fragile plastic housings during assembly. The inconsistent grip pressure results in damaged components, misalignment on the conveyor and downtime in the automated processes.

Delta Precision Ltd, an engineering subcontract business, has tasked your team with designing a new pneumatic gripper that:

- moves the small plastic component (shown) safely without causing damage;

- operates within a 6-bar air supply;

- has a maximum gripping force of 1.5N;

- fits within a 300 × 300 × 400 mm working envelope;

- works continuously for 8 hours without failure;

- remains within a £150 materials budget.

They wish to see an initial prototype in one week.

2. Task

Your task is to analyse the brief, plan a short engineering project, and propose a safe and reliable concept that meets all requirements.

This project will help you develop key engineering project management skills, including:

- interpreting and analysing a professional brief;

- applying tools such as Gantt charts, SMART goals, risk registers, and budgeting;

- justifying engineering decisions using technical and commercial reasoning;

- using contextualised maths and digital tools;

- reflecting on outcomes to identify improvements.

Deep interpretation of the workbook

Examiner reports show that students often lose marks because they:

- overlook key technical requirements;

- misunderstand the problem;

- ignore budget, space, or safety constraints;

- copy the brief without analysing it;

- include irrelevant information.

Prompts for students

- What exactly must the gripper do? What must it avoid doing?

- What limits are set by the factory environment?

- What specifications are fixed (e.g., pressure, gripping force, size, materials, shift length)?

- What commercial constraints apply (budget, cost of downtime)?

- What safety issues exist around pneumatics?

## Lesson 1 Activity 1 – Brief interpretation table

Read through the brief and extract all the requirements and constraints. Record these below in the correct category.

| Requirement category | Details identified |
| --- | --- |
| Technical requirements | - Must grip small plastic housings without cracking them. - Must operate using 6-bar pneumatic pressure. - Must have a maximum gripping force of 1.5N - Must fit within a 300 × 300 × 400 mm space. - Must provide consistent, repeatable grip force. - Should allow controlled opening/closing speed (may need flow control valve). |
| Commercial requirements | - Must stay within a £150 materials budget. - Should reduce waste caused by damaged parts. - Should increase throughput (fewer stoppages). - Should be low maintenance to reduce downtime. |
| Operational requirements | - Must operate for eight continuous hours without failure. - Must integrate with the existing conveyor system. - Must be reliable at high cycle rates. |
| Safety requirements | - Pneumatic components must handle 6 bar safely. - No pinch hazards for operators. - Must include pressure regulation to avoid dangerous over-force. - Must avoid sharp edges or exposed moving parts. |
| Constraints (time, budget, space, resources) | - Budget limit: £150 - Space/size limit: 300 × 300 × 400 mm - Existing air supply only (6-bar, no electrical redesign) - Time constraints of the short project |

Challenge question:
What assumptions must be checked before starting the design?

- That the supplied air pressure is actually stable at 6 bar.

- The exact dimensions and fragility of the plastic housing.

- Whether the gripper must rotate or only open/close in order to grip the component.

- The cycle time and required speed of operation.

- Whether materials (e.g., soft pads) are allowed by the client.

- Whether additional valves are available or must be included in the £150 budget.

## Lesson 1 Activity 2 – SMART project goals

Create one SMART goal for your project and explain how it fits the SMART criteria

Student prompts: - What EXACT performance target are you aiming for? - How will you measure success? - What time limit are you working within? - How do you ensure it is realistic?

Goal: Design a pneumatic gripper prototype within one week that handles plastic housings without damage using available materials within the £150 budget.

| SMART component | Your goal |
| --- | --- |
| Specific | Handles plastic housings without damage. |
| Measurable | Zero cracked parts during 20 test cycles. |
| Achievable | Uses available pneumatics and soft pads / stays within £150. |
| Relevant | Directly solves the client’s problem / Improves reliability. |
| Time-bound | Prototype completed within 1 week. |

Extension:
Explain how your SMART goal influences your planning decisions.

It sets a clear performance target (zero damaged parts), so my testing stage must include enough cycles to validate performance. The time-bound element ensures I set realistic task durations in my Gantt chart.

## Lesson 2 Activity 1 – Cost estimation

Estimate the cost of materials needed to produce a pneumatic gripper. Suggested materials are listed in the table below.

Remember, your design must remain under £150.

Student Prompts: - Which materials/components do you need? - What is the cheapest but still reliable option? - Are there optional parts you can remove?

| Item / Material | Unit Cost (£) | Quantity | Total (£) |
| --- | --- | --- | --- |
| Single-acting cylinder | £18 | 1 | £18 |
| Soft polymer grip pads | £5 | 2 | £10 |
| Flow control valve | £9 | 1 | £9 |
| Aluminium bracket | £12 | 1 | £12 |
| Fasteners & fixtures | £5 | 1 set | £5 |

Total Estimated Cost (£): 54

Budget Challenge:

Identify one cost-saving substitution (that you could make or have already made) and explain why it does not reduce product performance or safety.

Using a single-acting cylinder instead of a double-acting one saves £12–£15 and reduces complexity but still meets the performance needs because the gripper only needs force in one direction.

## Lesson 3 Activity 1 – Stakeholder mapping

Complete the table for the stakeholders involved in your project.

| Stakeholder | Interest in project | What they need from you | Potential conflicts |
| --- | --- | --- | --- |
| Client Apex Robotics | Reliable gripper that won’t damage parts; increased efficiency | A design that meets ALL requirements (6 bar, dimensions, safety, cost) | May push for faster delivery than feasible; may want lower cost |
| Subcontractor Delta Precision | Must supply a functioning, cost-effective solution | Clear technical specifications; timely updates; workable CAD models | May prioritise cost savings that affect performance |
| Regulator H&S Authorities | Safe pneumatic operation; compliance with pressure, risk and testing standards | Proper risk assessments; safe operating pressures; documentation | Safety requirements may increase cost/time |
| Project Team Engineers and designers | Clear plan, realistic deadlines, resources, safe working conditions | Defined roles, communication structure, achievable timeline | Team workload vs deadlines; resource limitations |
| End User Assembly line operators | Easy-to-use, ergonomic, reliable operation | A safe, intuitive gripper with consistent performance and no jamming | Their needs may add design complexity; training time constraints |

## Lesson 3 Activity 2 – Team roles structure

- Add three key responsibilities of each row to the table.

- Identify your own skills and strengths.

- Assign project roles to each member of your group. Record their initials against the role in the table and state the reasons why they were chosen.

Student prompts: - Who is best at scheduling? - Who has CAD skills? - Who is best at spotting risks and providing strategies to mitigate them?

| Role | Responsibilities | Assigned to | Reason |
| --- | --- | --- | --- |
| Project Manager | Scheduling, communication, deadlines | Student’s name / initials | Good communicator, organised |
| Design Engineer | Sketching, CAD, specification |  |  |
| Build Technician | Prototyping, assembly, testing |  |  |
| Safety Lead | Risk assessment, checks, compliance |  |  |
| Finance / Resource Lead | Budgeting, component sourcing, cost tracking |  |  |

Reflective question:
How should the team communicate progress or delays?

Provide updates at the end of each session, using a shared spreadsheet to track progress. If delays occur, the Project Manager adjusts the Gantt chart and reallocates tasks.

Lesson 4, Activity 1 – Concept development

1. Refer to Section 1: Introduction and Industry Context for the requirements of the pneumatic gripper.

2. Create 1–2 concept designs. Your design must include:

- labelled dimensions;

- explanation of the gripping mechanism;

- required pressure or force;

- chosen materials/supporting features.

3. Check that your design meets all these criteria.

Student prompts: - How does the mechanism open/close? - What materials are safest? - How will you ensure soft gripping?

Extension:
Include a simple force calculation to estimate grip pressure.

Assuming a 6mm piston has been used in the design.

- Calculate surface area using the formula: A=πr2

Radius = 3mm

A=π32  = 28.274mm2

- Calculate pressure using the formula:  Pressure = Force Area

Pressure = 1.5 N 28.274mm2    = 0.05305 MPa or 0.05305 x 106 Pa

- Convert pascals to bar: 105Pa = 1 bar

0.05305 x 106105 = 0.5305 bar

Pressure required to grip at 1.5N via a 6mm piston = 0.5305 bar

## Lesson 5 Activity 1 – Resource planning

Using your workbook, identify the resources your project would require.

| Resource type | What would be needed | Why this is important |
| --- | --- | --- |
| Time | 1 week to build a prototype Further time to test and evaluate design and build final product | Ensures tasks are realistic and fit within project deadlines |
| Budget | £150 limit for materials (tubing, fittings, cylinder, gripper pads) | Prevents overspending; aligns with commercial constraints |
| Human Resources | PM, Design Engineer, Build Technician, Safety Lead, Finance/ Resource Lead | Each role performs essential specialised tasks |
| Training Needs | Safe pneumatic handling, pressure testing procedures | Ensures safety + accuracy when working with compressed air |
| Communication Needs | Weekly PM updates, Teams chat, shared Gantt chart | Supports coordination, avoids miscommunication delays |
| Facilities / Equipment | Workshop tools, pneumatic test rigs, CAD workstation | Enables building and testing the prototype safely |

## Lesson 5 Activity 2 – Project planning using digital tools

Your project plan must include a digital Gantt chart.

This should show:

- all stages of the project;

- start/end dates;

- durations;

- dependencies;

- milestones;

- contingency (buffer time).

You may create your Gantt chart in:

- Excel / Google Sheets;

- a Gantt-chart generator;

- project management software.

Suggested task list

- Interpret brief

- Research relevant components

- Develop concept sketches

- Select materials and components

- Produce finished design

- Build prototype

- Test prototype

- Evaluate

- Present findings

Attach or insert your Gantt chart to this document.

Student prompts - Which tasks MUST be done first? - Which tasks depend on earlier tasks? - Where could delays happen? - What ‘buffer’ will you add? - What are the key milestones in the project that you will measure?

Key planning questions:

Which tasks depend on earlier tasks?

- Concept sketching depends on completing the brief interpretation.

- Testing depends on the prototype being assembled.

- Reflection depends on test results.

Which stages are most critical for the project to succeed?

- Correct interpretation of the brief.

- Assembly/testing (if delayed, everything else shifts).

- Purchasing/material selection (affects cost and feasibility).

What could delay the project?

- Waiting for materials.

- Difficulties assembling the prototype.

- Redesign required after testing reveals faults.

What should be included in a contingency plan?

- Add a 10–15% buffer to all task durations.

- Use backup materials if the preferred ones are not available.

- Have an alternative concept ready in case assembly fails.

## Lesson 6 Activity 3 – Justifying engineering decisions

Choose three decisions you have made in this project. For each example, justify your decision.

Student prompts: - How did you ensure your design met any safety requirements? - How have you ensured your design remains within budget? - How have you ensured your design limits any impacts on the environment?

Examples:

A single-acting cylinder was selected because it provides sufficient gripping force while reducing cost and air consumption.

The addition of soft polymer pads spreads the load over a wider area, preventing cracking.

A pressure regulator ensures the force does not exceed the material’s tolerance.

This combination of materials meets the performance requirements while staying within budget.

## Lesson 6 Activity 4 – Testing

Student prompts: - What are you testing? - How many cycles? - What counts as ‘success’?

If testing is not possible:

- perform a theoretical check using the sample testing data;

- compare your concept to the brief requirements;

- decide whether the test was successful and add to the notes section;

- identify next steps and add to the notes section.

If testing a prototype, complete the table below as you perform testing.

| Test | Expected outcome | Actual outcome | Notes |
| --- | --- | --- | --- |
| 10 grip cycles | No damaged parts | No damaged parts | Success |
| Opening/closing speed | Smooth, controlled | Slightly fast | Partial success Add flow control valve |
| Alignment test | Gripper holds parts centrally | Slight misalignment | Partial success Adjust pad shape |

## Lesson 6 Plenary – Reflection and evaluation

Look back through your completed workbook form.

If you were running a real project, how would you use the information identified throughout your planning process to evaluate how well the project went and identify areas of improvement for future projects?

| Information | Purpose |
| --- | --- |
| Brief interpretation table | Use as a checklist to check all requirements were met. |
| SMART objectives | Check the objectives were met and determine the overall success of the project. |
| Stakeholders mapping | Identify if the needs of each stakeholder were met and determine if any of the identified conflicts arose. |
| Team structure | Reflect on whether the team structure worked as planned or if roles overlapped. |
| Resource planning | Use as a checklist to check the project remained in budget / ordered the correct resources/ finished on time. |
| Project planning tools | Assess whether the Gantt chart was helpful and contained all the information needed to follow it. Determine if all risks were identified and managed appropriately. |