Activity 4 Create your own Gantt chart answers

In groups, you are going to plan the installation of a modular extension to a primary school.

The project must include renewable energy (solar PV), water conservation (rainwater harvesting), and be completed during the 30-day summer holiday period.

You have been given the following high-level schedule, which outlines tasks and durations.

| Task description | Duration |
| --- | --- |
| Site preparation & groundworks | 5 days |
| Delivery of modular units (including crane hire) | 2 days |
| Assembly of modular units on site | 7 days |
| Installation of solar PV system | 3 days |
| Installation of air source heat pump | 2 days |
| Installation of rainwater harvesting tank | 3 days |
| Internal fit-out (lighting, plumbing, finishes) | 5 days |
| Testing & commissioning (by manufacturers) | 2 days |
| Final inspection & handover | 1 day |

- Plan what you need to cover under these headings:

- Project title

- Key phases

- Trades involved

- Task dependencies

Answers might include:

- Project title: Environmentally-friendly primary school extension; Sustainable extension for a primary school

- Key phases: site preparation; access; off-site construction; on-site construction; installation – solar panels; installation – ASHP; installation – rainwater harvesting; internal works – lighting; internal works – plumbing; internal – first fit/second fit; internal – finishing & decorating; testing/compliance; handover

- Trades involved: plumbers, electricians, renewable energy specialists; off-site modular carpenters/assembly workers; on-site carpenters/assembly workers; painters & decorators

- Task dependencies: first to second fit electrical and plumbing works; weather for on-site assembly; final fix to inspection & handover

- Describe how your plan connects to wider industry considerations in order to create your supporting statement.

Answers might include:

| Health and safety | - Identified need for welfare set up - Risk assessments planned early - Identified need for PPE and signage - Identified compliance with regulations for site access and on-site safety |
| --- | --- |
| Specialist equipment | Solar panels (PV system) - mounting rails and anchoring system - resistance tester Water-efficiency measures - flow rate testing kit - pressure testing pump Rainwater harvesting - Mini excavator (for underground tank installation) - Submersible pump testing kit Air Source Heat Pumps (ASHP) - Vacuum pump (to remove moisture from system) - Digital thermometer or thermal probe (for commissioning checks) Modular construction equipment - Mobile crane (to position modular units) - Lifting frame/spreader beam |
| Contractors and job roles | General construction (Modular build) - Site manager - Crane operator - Groundworker Solar panel installation - Qualified electrician - Solar PV installer - Electrical tester / commissioning engineer Water efficiency & rainwater systems - Plumber - Drainage engineer Air Source Heat Pump installation - HVAC engineer - F-Gas certified refrigeration engineer - Electrician Design & compliance roles - Building services engineer - Architect or architectural technologist - Building control officer |
| Waste management | - Identifies need to follow Site Waste Management Plan - Identifies potential hazardous and non-hazardous materials - Include specific waste management costs and tasks |

c. Create a Gantt chart showing the sequence of tasks, durations and dependencies.

Answer

Sample structure for a Gantt chart.